## Appendix 1
APPENDIX 1
FORM OF TENDER
Contract 78012
Road & Pedestrian Safety Improvements on Guildford Way and David Avenue
SCHEDULE OF QUANTITIES AND PRICES
(see paragraph 5.3.1 of the Instruction to Tenderers)
(All Tender and Contract Prices shall NOT include GST. GST will apply upon payment)
(Should there be any discrepancy in the information provided, the City’s original file copy shall prevail)
ITEM NO. | MMCD Ref. / (Supp. Specs) | DESCRIPTION | UNIT | QTY | UNIT PRICE | EXTENDED AMOUNT
1 | 01 45 00S | QUALITY CONTROL
1.01 | (1.9) | Quality Control Testing | Incidental to Contract
2 | 01 55 00 | TRAFFIC CONTROL, VEHICLE ACCESS AND PARKING
2.01 | 1.5.1 | Traffic Control and Management | Incidental to Contract
3 | 01 57 01S | ENVIRONMENTAL PROTECTION
3.01 | (1.6.1) | ESC Supply & Installation, Maintenance and Removal | Incidental to Contract
SECTION 1 - GUILDFORD WAY AND FALCON DRIVE INTERSECTION
4 | 01 58 01S | PROJECT IDENTIFICATION
4.01 | (1.3.1) | 1.2m x 1.2m Static Construction Zone Information Sign | Each | 4
4.02 | (1.3.2) | Changeable Message Board Signs (2 Nos) | Month | 1
5 | 03 30 20S | CONCRETE WALKS, CURBS AND GUTTERS
5.01 | (1.4.5) | Concrete Sidewalk, Ramps - 100mm Thick (Base Gravel Included) | Square Meters | 115
5.02 | (1.4.3) | Concrete Median - 100mm Thick (Base Gravel Included) | Square Meters | 20
5.03 | (1.4.3) | Concrete Barrier Curb & Gutter (MMCD C5) (Incl. Gravels) | Lineal Meter | 80
5.04 | (1.4.10) | Tactile Strip - 24x60in - Access Tile, Yellow color - removable type | Each | 8
5.05 | (1.4.10) | Tactile Strip - 24x24in - Access Tile, Yellow color - removable type | Each | 4
6 | 31 11 01 | CLEARING AND GRUBBING
6.01 | (1.4.1) | Clearing & grubbing | Lump Sum | 1
7 | 31 24 13S | ROADWAY EXCAVATION, EMBANKMENT AND COMPACTION
7.01 | (1.8.5) | Common Excavation - Off-Site Disposal (Provisional) | Cubic Meters | 30
7.02 | (1.8.4) | Removal and Disposal of Existing Concrete Curbs | Lineal Meter | 80
7.03 | (1.8.4) | Removal and Disposal of Existing Concrete Median and Sidewalk | Square Meters | 110
7.04 | (1.8.4) | Removal and Disposal of Existing Asphalt Sidewalk | Square Meters | 25
7.05 | (1.8.10) | Overexcavation, Offsite Disposal, Backfilling (Provisional) | Cubic Meters | 5
8 | 32 17 23S | PAINTED PAVEMENT MARKINGS
8.01 | (1.5.4) | Signage, including reuse of existing signs | Lump Sum | 1
8.02 | (1.5.4) | Signal Operation Change Signs | Each | 2
9 | 33 44 01 | MANHOLES & CATCHBASINS
9.01 | (1.5.3) | Adjust existing manhole to finished grade | Lump sum | 2
10 | 34 41 13S | TRAFFIC SIGNALS
10.01 | 1.9.2 | Supply & Installation of Traffic Signals, junction boxes, and required ducting. All Works, Including any removal, adjustments and disposal needed to complete the work and as shown on the Contract Drawings | Lump Sum | 1
TOTAL FOR SECTION 1
SECTION 2 - GUILDFORD WAY AND LANSDOWNE DRIVE INTERSECTION
11 | 01 58 01S | PROJECT IDENTIFICATION
11.01 | (1.3.1) | 1.2m x 1.2m Static Construction Zone Information Sign | Each | 4
11.02 | (1.3.2) | Changeable Message Board Signs (2 Nos) | Month | 1
12 | 03 30 20S | CONCRETE WALKS, CURBS AND GUTTERS, AND DRIVEWAY
12.01 | (1.4.5) | Concrete Sidewalk, Ramps - 100mm Thick (Base Gravel Included) | Square Meters | 100
12.02 | (1.4.3) | Concrete Median - 100mm Thick (Base Gravel Included) | Square Meters | 20
12.03 | (1.4.3) | Concrete Barrier Curb & Gutter (MMCD C5) (Incl. Gravels) | Lineal Meter | 80
12.04 | (1.4.10) | Tactile Strip - 24x60in - Access Tile, Yellow color - removable type | Each | 8
12.05 | (1.4.10) | Tactile Strip - 24x24in - Access Tile, Yellow color - removable type | Each | 4
13 | 03 40 01S | PRECAST CONCRETE
13.01 | (1.4.6) | Re/Re Existing Allan Block Wall as required for signal base installation | Lump Sum | 1
14 | 31 11 01S | CLEARING AND GRUBBING
14.01 | (1.4.1) | Clearing & grubbing | Lump Sum | 1
15 | 31 24 13S | ROADWAY EXCAVATION, EMBANKMENT, & COMPACTION
15.01 | (1.8.5) | Common Excavation including off site disposal (Provisional) | Cubic Meters | 25
15.02 | (1.8.4) | Removal and Disposal of Existing Concrete Curbs | Lineal Meter | 80
15.03 | (1.8.4) | Removal and Disposal of Existing Concrete Median and Sidewalk | Square Meters | 110
15.04 | (1.8.10) | Over Excavation Including Offsite Disposal (Provisional) | Cubic Meters | 5
16 | 32 17 23S | PAINTED PAVEMENT MARKINGS & SIGNAGE
16.01 | (1.5.3) | Reinstating any damaged Thermoplastic Pavement Markings (extruded) | Lump Sum | 1
16.02 | (1.5.4) | Signage, including reuse of existing signs | Lump Sum | 1
16.03 | (1.5.4) | Signal Operation Change Signs | Each | 2
17 | 33 44 01S | MANHOLES & CATCHBASINS
17.01 | (1.5.3) | Adjust existing manhole to finished grade | Each | 1
18 | 34 41 13S | TRAFFIC SIGNALS
18.01 | 1.9.2 | Supply and installation of Traffic Signals, junctions boxes, and required ducting. All works, including any removal, adjustments and disposal needed to complete the work as shown on the Contract Drawings | Lump Sum | 1
TOTAL FOR SECTION 2
SECTION 3 - DAVID AVENUE PEDESTRAIN CROSSING (EAST OF PRINCETON AVENUE)
19 | 01 58 01S | PROJECT IDENTIFICATION
19.01 | (1.3.1) | 1.2m x 1.2m Static Construction Zone Information Sign | Each | 2
20 | 03 30 20S | CONCRETE WALKS, CURBS AND GUTTERS, AND DRIVEWAY
20.01 | (1.4.5) | Concrete Sidewalk, Ramps - 100mm Thick (Base Gravel Included) | Square Meters | 45
20.02 | (1.4.3) | Raised Concrete Buffer - 200mm Thick (Base Gravel Included) | Square Meters | 15
20.03 | (1.4.3) | Concrete Barrier Curb & Gutter (MMCD C5) (Incl. Gravels) | Lineal Meter | 35
20.04 | (1.4.10) | Tactile Strip - 24x60in - Access Tile, Yellow color - removable type | Each | 8
21 | 31 11 01S | CLEARING AND GRUBBING
21.01 | (1.4.1) | Clearing & grubbing, including Tree Removals <200mm dia | Lump Sum | 1
22 | 31 24 13S | ROADWAY EXCAVATION, EMBANKMENT, & COMPACTION
22.01 | (1.8.5) | Common Excavation including off site disposal (Provisional) | Cubic Meters | 55
22.02 | (1.8.4) | Removal and Disposal of Existing Concrete Curbs | Lineal Meter | 35
22.03 | (1.8.4) | Removal and Disposal of Existing Concrete Median and Sidewalk | Square Meters | 35
22.04 | (1.8.10) | Over Excavation Including Offsite Disposal (Provisional) | Cubic Meters | 5
23 | 32 01 16.7S | COLD MILLING
23.01 | (1.5.4) | Inlay Milling (Up to 50mm) (Provisional) | Square Meters | 60
24 | 32 11 23S | GRANULAR BASE
24.01 | (1.4.3) | MMCD 19mm Granular Base - For median and boulevard backfill (Provisional) | Tonnes | 85
25 | 32 12 16S | HOT-MIX ASPHALT CONCRETE PAVING
25.01 | (1.5.1) | Upper Course #1 Asphalt Concrete (50mm thick) - Inlay Milling areas (Provisional) | Tonnes | 10
26 | 32 17 23S | PAINTED PAVEMENT MARKINGS & SIGNAGE
26.01 | (1.5.3) | Line Painting & Thermoplastic Pavement Markings, including Eradication | Lump Sum | 1
26.02 | (1.5.4) | Signage, as shown on Contract Drawings | Lump Sum | 1
27 | 32 31 13S | CHAIN LINK FENCES AND GATES
27.01 | (1.5.4) | Handrail at Crosswalk (MMCD C14 Powder Coated Black) | Lineal Meter | 15
28 | 33 11 01S | WATERWORKS
28.01 | (1.8.4) | Removal of irrigation heads, adjustments to irrigation line, and cut and capping as required; including irrigation sleeving as per Irrigation Specifications | Lump Sum | 1
29 | 33 40 01S | STORM SEWER
29.01 | (1.6.12) | Removal of existing perforated PVC pipe and replacement with 150mm PVC DR28, tied into existing subdrain | Lineal Meter | 15
30 | 33 44 01S | MANHOLES & CATCHBASINS
30.01 | (1.5.3) | Storm Cleanout Relocation/Adjustment (Provisional) | Each | 3
31 | 34 41 13S | TRAFFIC SIGNALS
31.01 | 1.9.2 | Supply and installation of Rapid Rectangular Flashing Beacon, junction boxes, and required ducting. All works, including any removal, adjustments and disposal needed to complete the work as shown on the Contract Drawings | Lump Sum | 1
TOTAL FOR SECTION 3
Total Tendered Price - All Sections (exclude GST):
(Transfer the amount to Form of Tender Summary Page 1)
Name of Contractor: