City of Coquitlam

Request for Proposals

RFP No. 23-008

General Contractor Services for City Hall Annex Third Floor Renovations

Issue Date: January 10, 2023

TABLE OF CONTENTS

DEFINITIONS	4

1	INSTRUCTIONS TO PROPONENTS	5

1.1	Purpose	5

1.2	Non-mandatory Site Visit	5

1.3	Proposal Submission	5

1.4	Instructions to Proponents	5

1.5	Prices	7

1.6	Requested Departures	7

1.7	Evaluation Criteria	7

1.8	Eligibility	9

1.9	Completion Date	9

1.10	Bidders List	9

2	GENERAL CONDITIONS OF CONTRACT	10

2.1	Terms and Conditions of Contract	10

2.2	Permits and Regulations	10

2.3	Hours of Work	10

2.4	Regulatory and Compliance Requirements	10

2.5	Dangerous Materials	10

2.6	Operations and Coordination of the Services	10

3	SCOPE OF SERVICES	11

3.1	Scope of Work	11

3.2	Schedule	11

3.3	Location	12

3.4	Delivery, Storage, and Handling	12

3.5	Clean Up	12

Appendix A - CITY OF COQUITLAM SUPPLEMENTARY GENERAL CONDITIONS TO CCDC 2 - 2008

Appendix B – Architectural, Mechanical, Plumbing and Electrical Drawings

Appendix C - Project Specifications

PROPOSAL SUBMISSION

SUMMARY OF KEY INFORMATION

| RFP Reference | RFP No. 23-008 General Contractor Services for City Hall Annex Third Floor Renovations |
| --- | --- |
| Overview of the Opportunity | The City requests Proposals from experienced qualified firms to provide General Contractor Services for City Hall Annex Third Floor Renovations. |
| Closing Date and Time | 2:00 pm local time Monday, January 30, 2023 |
| Instructions for Proposal Submission | Proposals are to be consolidated into one PDF file and uploaded electronically through QFile, the City’s file transfer service accessed at qfile.coquitlam.ca/bid - In the “Subject Field” enter: RFP Number and Name - Add files in .pdf format and Send (Ensure your web browser remains open until you receive 2 emails from QFile to confirm receipt.) Phone 604-927-3060 should assistance be required. The City reserves the right to accept Proposals received after the Closing Date and Time. |
| Obtaining RFP Documents | RFP Documents are available for download from the City of Coquitlam’s website: https://www.coquitlam.ca/Bid-Opportunities Printing of RFP documents is the sole responsibility of the Proponents. |
| Instructions to Proponents | The guidelines for participation that will apply to this RFP are posted on the City’s website: Instructions to Proponents |
| Questions | Questions are to be submitted in writing quoting the RFP number and name up to 3 business days before the Closing Date sent to email: bid@coquitlam.ca |
| Addenda | Proponents are required to check the City’s website for any updated information and addenda issued, before the Closing Date at the following website: https://www.coquitlam.ca/Bid-Opportunities |
| Withdrawal of Submission | Proposals may be withdrawn by written notice only, made by an authorized representative of the Proponent sent to email: bid@coquitlam.ca prior to the Closing Date and Time. |
| Terms and Conditions of Contract | The City’s Standard Terms and Conditions - Purchase of Goods and Services, the City’s General Conditions, and the City of Coquitlam’s Supplementary General Conditions to the CCDC2-2008 Stipulated Price Contract will apply to the Contract awarded as a result of this RFP. |

DEFINITIONS

“City” “Owner” means City of Coquitlam;

“Contract” means the CCDC 2 – 2008 Stipulated Price Contract Between Owner and Contractor, as amended by the City’s Supplementary General Conditions to the CCDC 2 – 2008 and City Purchase Order that will be issued to formalize with the successful Proponent through negotiation process with the City based on the proposal submitted and will incorporate by reference the Request for Proposals, Specifications, Drawings, Appendices, any additional subsequent information, any addenda issued, the Proponent’s response and acceptance by the City.

“Contractor” means the person(s) firm(s) or corporation(s) appointed by the City to carry out all duties, obligations, work and services described in the Request for Proposal and all associated documentation, which may also include mutually agreed revisions subsequent to submission of a Proposal. Both “Contractor” and “Proponent” are complementary in terms of duties, obligations and responsibilities contemplated at the Request for Proposals stage, through evaluation process, execution and performance of the services and works.

“Price” means the amount that will be paid by the City to the Contractor for delivery and acceptance of goods and Services;

“Project Manager” means the City staff member appointed to coordinate the work;

“Proponent” means responder to this Request for Proposals;

“Proposal” means the submission by the Proponent;

“Request for Proposals” “RFP” shall mean and include the complete set of documents, specifications and addenda incorporated herein, and included in this Request for Proposals;

“Services” “Work” “Works” means and includes the provision by the successful Proponent of all services, duties, and expectations as further described in this RFP. This will also mean the whole of the work, tools, materials, labour, equipment, travel, and all that is required to be done, furnished and performed by the Contractor;

“Shall” “Must” “Will” “Mandatory” means a requirement that must be met;

“Site” means the place or places where the Services are to be performed

“Supply” “Provide” shall mean supply and pay for and provide and pay for.

# INSTRUCTIONS TO PROPONENTS

## Purpose

The City requests Proposals from experienced qualified firms to provide General Contractor Services for City Hall Annex Third Floor Renovations.

## Non-mandatory Site Visit

A non-mandatory site visit is scheduled for:

Date:	 January 18th, 2023

Time:	10:00 am

Location: Coquitlam City Hall Annex - Commercial entrance lobby

Address: Unit 301 - 3007 Glen Drive, Coquitlam (use the commercial entrance door, not the residential tower door).

## Proposal Submission

Proponents should complete and submit the information requested in this RFP document on the Proposal Submission Form or in a format that has been approved and is acceptable to the City.

## Instructions to Proponents

Proponents are advised that the rules for participation that will apply to this RFP are located: Instructions to Proponents.

By submission of a Proposal, the Proponent agrees and accepts the rules by which the RFP and selection process will be conducted.

- Proponents are responsible to inspect the existing site(s) and shall fully understand the difficulties and restrictions for execution of the work under this Contract. Interpretations by the Proponent of the meaning of any section of the Contract drawings and specifications herein prior to submitting a price for the Work shall not remove the responsibility of completing the Work as per the directions of the City, including all costs associated with that Work, should the Proponent’s interpretation be incorrect.

- Prior to submitting a price for the Work, the Proponent must seek clarification from the City for any items within the drawings and specifications that may appear to be unclear or conflicting.

- Prior to bidding, Proponents should visit, inspect, and familiarize themselves with the site(s) and of everything and of every condition potentially affecting the works to be executed, so that the execution of the Contract by the successful Proponent is founded and based upon the Proponent's own examination, information, and judgment. Failure to visit the site(s) prior to the Proposal Closing Date will in no way relieve the successful Proponent from the necessity of furnishing any material or performing any work that may be required to complete the work in accordance with the conditions and specifications without additional cost to the City.

- It shall be the responsibility of the Proponent, by personal inspection of the site(s) of the works, examination of the Contract documents, calculations, tests, and by requesting any required clarifications from the City, to become satisfied with respect to the quantities, quality, and practicability of the work. The Proponent must be aware that any information from the City was and is approximate and speculative only and cannot in any manner be warranted or guaranteed. If the Proponent fails to make a proper investigation and examination of the site(s) and the work they shall signify by entering into the Contract that they are willing to assume all risk of the work proving more onerous than was contemplated and/or assumed when the Contract was signed.

A complete set of RFP and Contract documents will include:

- Request for Proposals Documents

- Proposal Submission Form

- Appendix A - CITY OF COQUITLAM SUPPLEMENTARY GENERAL CONDITIONS TO CCDC 2 - 2008

- Appendix B – Architectural, Mechanical, Plumbing and Electrical Drawings

- Appendix C - Project Specifications

- Addendums as issued

- Figure dimensions of a drawing shall take precedence over measurements scaled from the drawing and large-scale drawings take precedence over those of a smaller scale. Supplementary drawings and specifications supersede their antecedents. Addenda drawings take precedent over all drawings. Addenda specifications take precedent over all specifications. In case of conflict between figured dimensions on a drawing and the dimensions of a specified product, the dimensions of the specified product will govern. The drawings and specifications complement each other and anything called for by one will be as binding as if called for by both.

- All information requested for the Proposal is to be completed by the Proponent on the supplied forms only and shall be based upon the whole of the specifications and Contract documents, without reservation. A Proposal that does not include all of the above sections, completed as specified herein, may be rejected.

- The selected Proposal shall supply all materials, equipment, installation, commissioning, and construction necessary for the successful starting and completion of the project in accordance with the drawings and specifications herein. It shall be the responsibility of the Proponent to include in the submitted Proposal amount sufficient amounts to cover the cost of the work and materials required to complete the Work but not specifically noted in the drawings and/or specifications. It is assumed that all taxes, duties and levies have been included in the Proposal amount.

- Complete sub-contracting of works will not be approved; however, segments of work involving special skills may be sub-contracted.

- The Proponent must indicate the names of the Proponent’s senior staff for the project, specifically identifying the project superintendent, and the names of the major sub-contractors and the work they will be performing.

- The Proponent must carefully examine the Proposal Documents and worksite(s). The Proponent may not claim, after the submission of a Proposal, that there was any misunderstanding with respect to the requirements and conditions imposed by the City.

- There will be no opportunity to make any additional claim for compensation or invoice for additional charges that were not considered and included in the Proposal price submitted, unless the City, at its sole discretion, deems that it would be unreasonable to do so, or there are additional work requirements due to unforeseen circumstances.

- All information in this RFP Document, Drawings, Specifications, Site Visit and Investigation, and any resulting Addenda will be incorporated into any Contract between the City and the successful Proponent, and therefore must be considered by the Proponent in preparing their Proposal.

## Prices

All Prices shall be all inclusive in Lump Sum Form (Canadian Funds) exclude GST and shall remain FIRM for the completion of the Services.

## Requested Departures

The Proponent acknowledges that the departures requested in the Proposal Submission Form will not form part of the Contract unless and until the City specifically consents in writing to any of them. The City may not consider any departures not stated in the Proponent’s Proposal Submission.

## Evaluation Criteria

Evaluation Criteria of each proposal will be determined in accordance with the following:

| Proposal Evaluation Summary | Maximum Points to be Awarded |
| --- | --- |
| Corporate | 30 |
| Technical | 30 |
| Financial and Value Added | 40 |
| Total | 100 |

The criteria for evaluation of the Proposals may include, but is not limited to:

Corporate Experience, Reputation, Capacity and Resources

- Established business and demonstrated performance providing services of similar size, scope and complexity

- References (on-time completion, performance, within budget, etc.)

- Sub-contractors

- Staff qualifications and experience

Technical

- Methodology, set-up and execution of the work

- Disposal and reuse

- Ability to comply with the stated specifications and requirements

- Schedule and Completion Date

- Risk factors

- Quality Assurance and Safety

Financial and Value Added

- Total Price, Price for Optional work and Additional Labour Rates

- Value Added / Sustainable benefits

These criteria will be used to determine best overall value to the City. Proposals will be compared to select one or more that are most advantageous.

And, upon selection of one or more lead Proponent(s):

- References may be contacted

- Interviews may be conducted

The City reserves the right to check references on other projects even if they are not specifically listed. Information obtained from references will be confidential and will not be disclosed to any Proponents.

These criteria will be used to determine best overall value to the City as well as any other criteria that may become evident during the evaluation process.

The City may, at its discretion, request clarification or additional information from a Proponent with respect to any Proposal and the City may make such requests to only selected Proponents. The City may consider such clarifications or additional information in evaluating a Proposal.

Incomplete Proposals or Proposals submitted on forms other than the Proposal Form may be rejected.

Proponents agree the City may disclose names of Proponents and total award amount, however, unevaluated results, unit prices, rates or scores will not be provided to any Proponents.

The City reserves the right to reject without further consideration any Proposal which in its opinion does not meet the criteria it considers essential for the work outlined in this RFP.

Where only one Proposal is received, the City may reject such and re-issue the RFP on a selected basis.

Prices shall include the provision of all tools, materials, equipment, labour, transportation, fuel, supervision, management, overhead, materials, traffic control, services, all necessary packing and crating (where applicable), Canadian Customs import and export duties, freight, handling, transportation, insurance, all other associated or related charges, foreign, federal, provincial and municipal taxes, bonding costs, all licences, permits, inspections and all other requirements necessary for the commencement, performance and completion of Services as described.

## Eligibility

For eligibility, and as a condition of award, the successful Proponent would be required to meet or provide the equivalent:

- Commercial General Liability (CGL) insurance $5M coverage provided on the City's Standard Insurance Form

- Prime Contractor Designation Form and be responsible for all the work at the site in accordance with WCB regulations

- Be registered and provide WorkSafeBC clearance

- Accept the City’s standard Terms and Conditions posted on the City’s website: Standard Terms and Conditions - Purchase of Goods and Services

- A City of Coquitlam or Tri Cities Intermunicipal Business License

- Enter into a Contract with the City using the CCDC 2-2008 document.

## Completion Date

The Work shall be completed by July 28, 2023

## Bidders List

The City does not retain a list of interested contractors (“Bidders List”). Interested contractors are encouraged to register as plan takers and may view the RFP Documents and Drawings by contacting the Vancouver Regional Construction Association (“VRCA”), website : www.vrca.ca , ph: 604- 294-3766 or email: info@vrca.ca quoting the Coquitlam RFP Reference Number.

# GENERAL CONDITIONS OF CONTRACT

## Terms and Conditions of Contract

The City’s Standard Terms and Conditions - Purchase of Goods and Services , as published on the City’s website, the Conditions listed below, the Request for Proposals Documents, Appendices, along with the accepted Proposal, addenda and any subsequent clarifications, correspondence, the CCDC 2 – 2008 Stipulated Price Contract Between Owner and Contractor, as amended by the City’s Supplementary General Conditions to the CCDC 2 – 2008 and City Purchase Order that will be issued to formalize with the successful Proponent through negotiation process with the City based on the proposal submitted and will incorporate by reference the Request for Proposals, Specifications, Drawings, Appendices, any additional subsequent information, any addenda issued, the Proponent’s response and acceptance by the City, the totality of which will constitute the Contract.

PROJECT SPECIFIC TERMS AND CONDITIONS

## Permits and Regulations

The Contractor is to obtain permits, pay all fees therefore and comply with all Provincial, Municipal and other legal regulations and by-laws applicable to the work. If no local regulations, comply with the National Building Codes of Canada, latest revision. Workers Compensation Act and Workplace Hazardous Material Information System (“W.H.M.I.S.”) requirements and regulations are to be strictly adhered to.

## Hours of Work

Unless otherwise specified the Contractor shall carry out the work during regular business hours, and in compliance with the City’s Noise Bylaw (Monday to Friday – 7 a.m. to 8 p.m. and Saturdays – 9 a.m. to 6 p.m.) and Strata’s Bylaws ( Monday to Friday 8:00 a.m. to 5:00 p.m. and Saturday 10:00 a.m. to 5:00 p.m.). Permits will be required for work outside of normal working hours. The Contractor shall be responsible for obtaining any such permits.

## Regulatory and Compliance Requirements

Contractor is to comply with the latest British Columbia Building Code, and Canadian Electrical Code, including all provincial and other amendments, and local by-laws. When multiple codes and/or regulations apply, follow the most stringent provision:

- Canadian Standards Association (CSA)

- Canadian Electrical Code (CE)

- Worker’s Compensation Act;

## Dangerous Materials

Any and all dangerous or hazardous materials removed from the site are to be separated and disposed of in accordance with all applicable policies, guidelines and standards from authorities having jurisdiction.

## Operations and Coordination of the Services

The Contractor shall agree to coordinate the execution of the Services with the City such that disruption of the Work of all involved is minimized.

# SCOPE OF SERVICES

The scope of services includes, but is not limited to, provision of all labour, supervision, equipment, tools, materials, transportation, and incidentals necessary for the demolition, supply, delivery, and installation as stated within this RFP along with:

- Appendix B – Architectural, Mechanical, Plumbing and Electrical Drawings

- Appendix C – Project Specifications

## Scope of Work

Room 301 of City Hall Annex is being renovated from its current configuration, which is setup as a co-working space to a more optimized office space to accommodate City staff.

Project Scope includes but not limited to:

- Demolish and remove existing interior walls, doors, floor finish, ceilings, millwork, and light fixtures as detailed in the drawings package attached in Appendix B.

- Carefully remove and re-use ceiling hung acoustic baffles and light fixtures as noted in the drawings package.

- Demolish existing light fixtures as shown on drawing package.

- Demolish, remove and cap existing plumbing fixtures, equipment and piping.

- Demolish, remove or relocate existing mechanical ducts and vents.

- Patch and repair areas affected by the demolition to match existing or new conditions.

- Construct new steel stud framed walls to form individual offices, open work space, meeting rooms and lunch room.

- Construct and install new ceiling and floor finishes.

- Firestop around existing and new floor and wall penetrations as necessary in compliance with the Code.

- Provide scanning for new plumbing risers through floor. Confirm location is compatible with structural slab bands.  Drilling to be done outside normal operating hours of staff on the floor below (8:00 am-5:00 pm) and be coordinated with the tenants. Protection and cleaning of staff area to be included. (Note: Permits will be required for works performed outside of normal working hours as noted in Strata and City Bylaws).

- Obtain written approval from the structural consultant before cutting or burning through structural members.

- Modify sprinkler system and provide new sprinkler heads to suit new layout and ensure compliance with Code. New sprinkler heads shall match the base building standard.

- Install new mechanical ducts, dampers, supply and exhaust vents as necessary.

- Install new light fixtures and fire safety components.

- Access through elevator and loading bay may be restricted. Large items may require to be transported through an exterior balcony located on the southwest corner of the unit (facing west). Road/sidewalk closure permit and or building strata approval may be required.

## Schedule

The Contractor to provide a project construction schedule prior to the start of construction. The schedule must identify all the necessary start and completion dates of construction, construction activities, submittals process activities, material deliveries, and other milestones required to give a complete review of the project.

## Location

City Hall Annex located at:

Unit 301 - 3007 Glen Drive

Coquitlam, B.C.

## Delivery, Storage, and Handling

All materials and equipment to be new. Deliver and store materials in original, unopened packaging. Assume all packing, transportation, and insurance costs.

All packaging material must be removed from site at the Contractor’s expense.

Store materials in a safe and secure location, and protect against damage. City is not responsible for loss, damage or theft of material or equipment.

## Clean Up

At the end of each day and at the conclusion of work, the Contractor shall promptly remove any of his/her equipment or materials and leave the site(s) in a clean and cleared condition.

APPENDIX A

CITY OF COQUITLAM

SUPPLEMENTARY GENERAL CONDITIONS

TO CCDC 2 - 2008

SUPPLEMENTARY GENERAL CONDITIONS

STIPULATED PRICE CONTRACT CCDC 2 2008

These Supplementary General Conditions modify and amend Standard Construction Document CCDC-2 – 2008 and form a part of this Contract.

In the event of any conflict between the provisions of the Standard Construction Documents and any provision of these Supplementary General Conditions, these Supplementary General Conditions shall govern.

Standard Construction Document CCDC-2—2008 is amended as follows:

AGREEMENT BETWEEN OWNER AND CONTRACTOR

ARTICLE A-3 CONTRACT DOCUMENTS

- The Agreement is amended by including “Part C – Schedule 1 - City of Coquitlam Certificate of Insurance Form – Construction”.

ARTICLE A-5 PAYMENT

- The Agreement is amended by deleting Article A-5.3, including all of 5.3.1 and 5.3.2, in its entirety.

NEW ARTICLE

- The Agreement is amended by adding the following new Article after Article A-8:

ARTICLE A-9 TIME OF THE ESSENCE

9.1 	All time limits stated in this Contract are of the essence of the Contract.

GENERAL CONDITIONS OF THE STIPULATED PRICE CONTRACT

PART 1 GENERAL PROVISION

GC 1.1 CONTRACT DOCUMENTS

- Section 1.1.8 is amended by replacing the term “sufficient copies” with “a pdf copy”.

- Section 1.1 is amended by adding the following new subsection:

1.1.11 		The Contractor is responsible for the installation and the coordination of metric and imperial dimensioned products and materials as may be applicable.

PART 2 ADMINISTRATION OF THE CONTRACT

GC 2.1 AUTHORITY OF THE CONSULTANT

- Section 2.1 is amended by adding a new subsection after subsection 2.1.3 as follows:

2.1.4	If a Consultant is not engaged on the Project, the Owner will fulfill the requirements of a Consultant.

GC 2.3 REVIEW AND INSPECTION OF THE WORK

- Section 2.3 is amended by adding a new subsection after subsection 2.3.7 as follows:

2.3.8	Should the Consultant be required to make more than one review of rejected work or should the Consultant perform additional reviews due to failure of the Work to comply with the contract documents, the Contractor is required to compensate the Owner for such additional Consultant services, including expenses incurred.  Adjustments for such compensation should be made as outlined under Part 6 CHANGES IN THE WORK.

PART 3 EXECUTION OF THE WORK

G.C. 3.5 CONSTRUCTION SCHEDULE

- Section 3.5 is amended by adding the following new subsection after subsection 3.5.1.3:

3.5.1.4	The Contractor will perform the Work in compliance with the construction schedule.  If, for any reason, the Work falls behind the schedule for the Work set forth in the construction schedule the Contractor shall as part of the Work either:

(a)	if in accordance with the Contract Documents the delay entitles the Contractor to a time extension the Contractor shall forthwith prepare and deliver to the Consultant a revised construction schedule to the reasonable satisfaction of the Consultant indicating the revised dates for the remaining activities of the Work; or

(b)	if in accordance with the Contract Documents the delay does not entitle the Contractor to a time extension then the Contractor shall take such steps as required to bring the Work back into conformity with the construction schedule.

Failure to comply with the requirements of this section shall be deemed to be a default under the Contract to which the provisions of GC 7.1.2 apply.

GC 3.6 SUPERVISION

- Subsection 3.6.1 is amended by adding the following sentence at the end of the subsection: “The appointed Contractor representative shall not change without consultation with and written acceptance of the Owner, which acceptance will not be unreasonably withheld.”

GC 3.7 SUBCONTRACTORS AND SUPPLIERS

- Subsection 3.7.2 is amended by adding the following sentence at the end of the subsection: “The Contractor shall not employ any Subcontractor, or change Subcontractor, without the written approval of the Owner, which approval will not be unreasonably withheld.”

- Subsection 3.7.3 is deleted in its entirety and replaced with the following:

3.7.3	If the Owner reasonably objects to the performance, qualifications, experience or suitability of any of the Contractor’s personnel, Subcontractors or Suppliers, then the Contractor will, on written request from the Owner, replace such personnel, Subcontractor or Supplier immediately.

- Section 3.7 is amended by adding the following new subsections after subsection 3.7.6:

3.7.7	The Contractor will provide only personnel who have qualifications, experience and capabilities to perform the Work.

3.7.8 	The Contractor shall coordinate the Work of all of its Subcontractors and Suppliers and determine to what extent Work specified in each section of the specifications is effected by Work indicated elsewhere and make all necessary allowances for their integration.  All additional Work resulting from the failure to make such determination shall be done at no cost to the Owner.

3.7.12 	The Contractor shall indemnify and hold harmless the Owner, its agents, servants and employees, from and against all costs, claims, damages, debts, sums, actions and causes of action whatsoever and whensoever arising out of any claim of lien or action by a Subcontractor, Supplier or labourer with whom the Contractor or any of its Subcontractors or Suppliers has contracted in relation to the Work.

GC 3.8 LABOUR AND PRODUCTS

- Subsection 3.8.2 is amended by adding the following after “consultant”: “Products which are not specified shall conform to current applicable specifications and regulations of the Canadian Standards Association, Technical Builders' Bulletin, Canadian Government Specifications Board, National Building Code, British Columbia Building Code, American Society for Testing and Materials, Trade Association Specifications and all authorities having jurisdiction at the Place of the Work.”

- Section 3.8 is amended by adding the following new subsections after subsection 3.8.3:

3.8.4	Immediately upon receiving from the Consultant or the Owner a written notice stating the Consultant’s or the Owner’s reasonable objection to the work conduct of any superintendent, foreman or worker on the Project site, the Contractor will remove such persons from the Project site.

3.8.5 	No person shall with relation to his employment or eligibility for employment be discriminated against by reason of his or her race, colour, ancestry, place of original, political belief, religion, marital status, family status, physical or mental disability, sex, sexual orientation or age, or because he or she has been convicted of a criminal or summary conviction offence that is unrelated to the employment.

3.8.6 	The Contractor shall supply labour that is compatible with other labour employed on the Work. In the event of labour disputes arising from the provision of skilled or unskilled labour by the Contractor or its Subcontractors, the Contractor shall, to the satisfaction of the Owner or Consultant, as applicable,, make such arrangements as are necessary to preclude delay to the Work or to the work of others at the Project Site.

GC 3.9 DOCUMENTS AT THE SITE

- Subsection 3.9.1 is amended by inserting the words “reviewed shop drawings” immediately after “Contract Documents”.

- Section 3.9 is amended by adding the following as a new subsection after subsection 3.9.1:

3.9.2	Record drawings to be maintained and available to view by Consultant and Owner.

GC 3.10	 SHOP DRAWINGS

- Section 3.10 is amended by adding the following new subsections after subsection 3.10.12:

3.10.13	Upon Substantial Performance of the Work, the Contractor will submit all reviewed and revised Shop Drawings to the Owner as a permanent record of the Work.  As of the date of issuance of a final certificate for payment, the Shop Drawings will be retained by the Owner as the Owner’s property.

3.10.14	Electronic submissions and electronic review stamp by the Consultant are acceptable.

GC 4.1 CASH ALLOWANCES

- Subsection 4.1.4 is amended by:

a)	In all instances deleting the words “any cash allowance”, and replacing them with “all cash allowances”.

b)	At the end of the last sentence, adding the following new sentence: “The Contractor’s overhead and profit on costs exceeding the amount of the allowance shall be ten (10%) percent on Work performed directly by the Contractor, and five (5%) percent on Work performed by Subcontractors.”

- Section 4.1 is amended by add the following new subsection after subsection 4.1.7:

4.1.8	Expenditures of the cash allowance are to be directed as per GC 6.2 CHANGE ORDER or GC 6.3 CHANGE DIRECTIVE, at the Owner’s directive. All Work under cash allowance is to be competitively bid unless directed by the Owner. The Contractor shall keep records and submit a monthly update on expenditures of a cash allowance, including all unallocated amounts.

PART 5	PAYMENTS

GC 5.1	 FINANCING INFORMATION REQUIRED OF THE OWNER

- Section 5.1 is deleted in its entirety.

GC 5.2	APPLICATIONS FOR PROGRESS PAYMENT

- Subsection 5.2.3 is amended by:

a) 	Deleting “and Products delivered to the Place of the Work”; and

b) 	Adding the following at the end of the subsection: “The Contractor will identify separately, with reference to the applicable Change Order, any application for payment for Work performed pursuant to a Change Order.  No payment for extras or changes will be made before the issuance of the applicable Change Order.”

- Subsection 5.2.7 is deleted in its entirety and replaced with:

5.2.7	No claim shall be made for any Product which is delivered to the Place of the Work until it is incorporated into the Work and any claim for Products which are incorporated into the Work shall be supported by such evidence as the Consultant may reasonably require to estimate the value of such Products.

- Section 5.2 is amended by adding the following new subsections after subsection 5.2.7:

5.2.8	A draft application for payment is to be submitted to the Owner on the 25th of the month.

5.2.9	An application for payment shall be deemed received only if submitted complete with required supporting documentations as determined by the Owner.

GC 5.3 	PROGRESS PAYMENT

- Subsection 5.3.1.3 is deleted in its entirety and replaced with:

5.3.1.3	The Owner shall use its best efforts to make payment to the Contractor on account as provided in Article A-5 of the agreement, such payment to be net 30 days from the date on which the invoice is delivered to the Owner.

- Section 5.3 is amended by adding the following new subsections after subsection 5.3.1:

5.3.2	The Owner may set off from payments owing to the Contractor costs, expenses and damages the Owner incurs or suffers as a result of the Contractor’s wrongful or negligent act or omission, or which the Owner incurs on the Contractor’s behalf.

5.3.3	The Owner may, in addition to other holdbacks as provided by the Contract Documents, hold back an amount equal to any lien which has been filed with respect to the Work, plus 10% as security for costs.  The Owner may, at its option, after five days written notice to the Contractor, pay such amount into court to discharge the lien.  If the lien is discharged without payment of the holdback into court, then the Owner shall pay such holdback to the Contractor, without interest.

5.3.4	In addition to builders lien holdbacks, the Owner may retain holdbacks to cover deficiencies in the Work, in an amount equal to twice the amount the Consultant or Owner estimates as the total cost to complete the deficiencies and three times the amount if less than $10,000.

GC 5.4 	SUBSTANTIAL PERFORMANCE OF THE WORK

- Section 5.4 is amended by:

a) 	Adding the words “or Owner” after the word “Consultant” in subsection 5.4.2 and 5.4.3; and

b) 	Adding the following new subsection after subsection 5.4.3:

5.4.4 	Should the Consultant or Owner find significantly more incomplete or deficient Work than those listed by the Contractor with its application, the Consultant or Owner may elect to terminate its inspection and to not issue a certificate of Substantial Performance. If the Consultant or Owner terminates its inspection, the Contractor shall compensate the Owner for the additional time and expenses incurred by the construction manager, Consultant, Subconsultants and Owner in relation to multiple inspections.

GC 5.5 PAYMENT OF HOLDBACK UPON SUBSTANTITAL PERFORMANCE OF THE WORK

- Subsection 5.5.3 is deleted in its entirety.

GC 5.7 FINAL PAYMENT

- In subsection 5.7.4, the words “no later than 5 days after the issuance of a final certificate for payment” are deleted and replaced with “net 30 days from invoice date, on a best effort basis”.

- Section 5.7 is amended by adding the following new subsection after subsection 5.7.4:

5.7.5	The issuance of a final certificate for payment in no way relieves the Contractor from correcting defects or deficiencies not apparent at the time the certificate is issued.

PART 6	CHANGES IN THE WORK

GC 6.1	OWNER’S RIGHT TO MAKE CHANGES

- Subsection 6.1.2 is amended by adding the following to the end of the sentence: “[…] or written approval to proceed.”

GC 6.2 CHANGE ORDER

- Subsection 6.2.1 is amended by adding the following at the end of the subsection: “A Change Order shall be a final determination of adjustments in the Contract Price, Contract Time or both, as applicable.  There shall be no adjustment to the Contract Price or Contract Time should the Contractor fail to present a request for a specific adjustment in response to a notice describing a proposed change in the Work.”

- Subsection 6.2.2 is amended by adding “[…] and be noted on the Change Order schedule of values” at the end of the sentence.

- Section 6.2 is amended by adding the following new subsection after subsection 6.2.2:

6.2.3	The value of a change in the Work shall be determined in one or more of the following methods as selected by the Consultant in consultation with the Owner:

(a)	By estimate and acceptance in a lump sum;

(b)	Where unit prices are set out in the Contract Documents or subsequently agreed upon, in accordance with such unit prices;

(c)	By costs and a percentage fee for overhead and profit as calculated below:

    - For Change Orders not covered by allowances, the Contractor’s overhead and profit and supervision shall be 10% on Work performed directly by the Contractor, and 5% on work performed by Subcontractors;

    - The Subcontractor’s allowance for overhead and profit and supervision shall be 10% of the actual cost of all Change Orders attributed to the Subcontractor’s Work, as determined by this paragraph;

    - Where the Change Order involves the substitution of one type of Product for another the “actual cost” of the Change Order, whether credit or extra, shall be the net difference in the “actual cost” defined above.

GC 6.3 CHANGE DIRECTIVE

- Subsection 6.3.7.1 is amended by adding the word “construction” before “personnel”, and after “personnel” adding: “[…] excluding administrative, clerical and supervisory personnel, and for only the portion of their time required for the Work attributable to the change.”

- Section 6.3. is amended by adding the following new subsection after subsection 6.3.13:

6.3.14	all other costs attributable to the change in the Work including the costs of all administrative or supervisory personnel are included in overhead and profit calculated in accordance with the provisions of section 6.2.3 of GC6.2 CHANGE ORDER.

GC 6.4 CONCEALED OR UNKNOWN CONDITIONS

- Section 6.4 is amended by adding the following new subsection after subsection 6.4.4:

6.4.5	The Contractor acknowledges that it has inspected the Place of the Work for the physical conditions described in GC 6.4.1 and has disclosed its findings to the Owner.  The Contractor agrees not to seek any increases in the Contractor’s cost or time to perform the Work in respect of any conditions that were or ought to have been discovered upon reasonable inspection by the Contractor prior to the date of the Contract.

GC 6.5 DELAYS

- Subsection 6.5.4 is amended by adding the following at the end of the subsection: “[…]. No claim for additional time arising from a delay will be applicable to the Contractor unless the Contractor has prepared, or caused to be prepared, records of all Work and the costs of the Work, on a daily basis as the Work proceeds, and submits such records in support of the claim.”

GC 6.6 CLAIMS FOR A CHANGE IN CONTRACT PRICE

- Subsection 6.6.5 is amended by adding the following at the end of the subsection: “[…]. No claim for additional payment arising from a delay will be payable to the Contractor unless the Contractor has prepared, or caused to be prepared, records of all Work and the costs of the Work, on a daily basis as the Work proceeds, and submits such records in support of the claim.”

PART 7 DEFAULT NOTICE

GC 7.1 OWNER’S RIGHT TO PERFORM THE WORK, TERMINATE THE CONTRACTOR’S RIGHT TO CONTINUE WITH THE WORK OR TERMINATE THE CONTRACT

- Subsection 7.2.3.1. is deleted in its entirety.

PART 8 DISPUTE RESOLUTIONS

GC 8.2 NEGOTIATION, MEDIATION AND ARBITATION

- Section 8.2 is deleted in its entirety and replaced with the following:

8.2.1	The parties will make reasonable efforts to resolve any dispute, claim, or controversy arising out of this Contract or related to this Contract (“Dispute”) using the dispute resolution procedures set out in this section.

Negotiation

The parties will make reasonable efforts to resolve any Dispute by amicable negotiations and will provide frank, candid and timely disclosure of all relevant facts, information and documents to facilitate negotiations.

Mediation

If all or any portion of a Dispute cannot be resolved by good faith negotiations within 30 days, either party may, by delivery of written notice to the other party, refer the matter to mediation.  Within 7 days of delivery of the notice, the parties will mutually appoint a mediator.  If the parties fail to agree on the appointment of the mediator, then either party may apply to the British Columbia International Commercial Arbitration Centre for appointment of a mediator.  The parties will continue to negotiate in good faith to resolve the Dispute with the assistance of the mediator.  The place of mediation will be Coquitlam, British Columbia.  Each party will equally bear the costs of the mediator and other out-of-pocket costs, and each party will bear its own costs of participating in the mediation.

Litigation

If within 90 days of the request for mediation the Dispute is not settled, or if the mediator advises that there is no reasonable possibility of the parties reaching a negotiated resolution, then either party may without further notice commence litigation in the metro Vancouver area.

PART 9 - PROTECTION OF PERSONS AND PROPERTY

G.C. 9.1 PROTECTION OF WORK AND PROPERTY

- Section 9.1 is amended by adding the following new subsection after subsection 9.1.4:

9.1.5	In the event of a delay or shut down which results in a stoppage of the Work, the Contractor shall take all reasonable steps to protect the Work for the entire period of the delay or shut down.  The cost of such protection shall be paid as follows:

- if under 6.5.1, or 6.5.2, the Owner will pay,

- If under 6.5.3, the Contractor will pay.

PART 11 – INSURANCE AND CONTRACT SECURITY

G.C. 11.1 INSURANCE

- Section 11.1 is deleted in its entirety and replaced with the following:

11.1.1	The Contractor shall, without limiting its obligations or liabilities under this Contract or otherwise, and at its own expense, provide and maintain for the duration of the Contract Time and the applicable warranty period, insurance policies in the following forms and amounts:

(a)	commercial general liability insurance on an occurrence basis, in an amount not less than five million ($5,000,000) dollars inclusive per occurrence against death, bodily injury and property damage arising directly or indirectly out of the Work or operations of the Contractor, its employees and agents;

(b)	automobile liability insurance on all vehicles owned, operated or licensed in the name of the Contractor in an amount not less than two million ($2,000,000) dollars per occurrence for bodily injury, death and damage to property; and

(c)	all risk contractors equipment or property insurance covering all equipment owned or operated by the Contractor or its agents or employees for the performance of the Work, for all risks of loss or damage with coverage in such amounts and on such terms as to allow for immediate replacement.

(d)	builders risk and wrap up liability for the value of the project for 24 months completed operations. The Contractor is responsible to pay for the premiums and deductible amounts to cover all risks of loss or damage with coverage in such amounts and on such terms as to allow for immediate replacement.

11.1.2	All insurance policies required under this Contract must:

(a) 	Name the Owner and School District #43 Coquitlam as an additional insured;

(b)	Be primary and not require the sharing of any loss by the Owner or any insurer of the Owner;

(c)	Include cross liability and severability of interests’ clauses such that the coverage shall apply in the same manner and to the same extent as though a separate policy had been issued to each insured;

(d)	Include, but not be limited to: premises and operators’ liability, broad form products and completed operations, Owner’s and Contractor’s protective liability, blanket contractual, employees as additional insureds, broad form property damage, non-owned automobile, contingent employers’ liability, broad form loss of use, personal injury, and incidental medical malpractice;

(e)	Be endorsed to provide the Owner with at least 30 days advanced written notice of cancellation or material change restricting coverage;

(f)	Be issued by insurers licensed to conduct business in British Columbia.

11.1.3	In the event the insurance requirements specified in the City of Coquitlam Insurance Certificate Form—Construction, attached to the Contract differs from the requirements in section 11.1.1 above, then the provisions of the City of Coquitlam Insurance Certificate Form shall prevail.

11.1.4	The Contractor shall provide the Owner with evidence of the required insurance prior to commencement of the Work and as requested by the Owner from time to time.

PART 12 – INDEMNIFICATION, WAIVER OF CLAIMS, AND WARRANTIES

G.C. 12.1 INDEMNIFICATIONS

Section 12.1 is deleted in its entirety and replaced with the following:

12.1.1	The Contractor will indemnify and save harmless the Owner, its employees and agents, including the Consultants, from and against any and all losses, claims, damages, action, causes of action cost and expenses that the owner may sustain, incur, suffer or be put to at any time either before or after the expiration or termination of this Contract, where the same or any of them are based upon, arise out of or occur, directly or indirectly, by reason of any act or omission of the Contractor pursuant to this Contract, excepting always liability arising out of the independent negligent acts of the Owner.

12.1.2	At the Owner’s option, the Contractor shall, at his own expense, promptly assume the defense of any claim, suit or any other proceeding and promptly pay any and all costs that may be incurred by or against the Owner.  The Owner may, as a condition precedent to any payment hereunder, require the Contractor to submit waivers or releases extinguishing all claims of any person, firm or corporation.

12.1.3	If any encumbrance be placed upon or obtained against the property comprising the site of the Work, or as a result of any such suit or proceeding, the Contractor shall forthwith cause the same to be discharged.  In the event that the Contractor fails to remove the said encumbrance(s), the Owner may pay whatever monies are necessary to fully discharge these encumbrances and all of its cost in that regard may be deducted from monies otherwise payable to the Contractor.

GC 12.2 WAIVER OF CLAIMS

- Subsections 12.2.3, 12.2.4, 12.2.5, 12.2.9 and 12.2.10 are deleted in their entirety and subsections 12.2.6, 12.2.7 and 12.2.8 renumbered accordingly.

GC 12.3 WARRANTY

- Subsections 12.3.1 and 12.3.6 are deleted in their entirety.  Subsection 12.3.1 is replaced with the following:

12.3.1 	The warranty period under the Contract is one year from the date on which final certificate of payment is issued by the Owner under subsection 5.7.3.

- Subsection 12.3.3 is deleted and replaced with the following:

12.3.3 	The Owner, through the Consultant, shall promptly give the Contractor Notice in Writing of observed defects and deficiencies which occur during the one year warranty period, which Notice in Writing may specify the time within which the defects or deficiencies must be rectified.  Defects or deficiencies shall include, but not be limited to, shrinkage, expansion and movement.

- Subsection 12.3.4 is amended by adding the following at the end of the subsection: “The Contractor shall make good all deficiencies within such time period as specified in the Notice of Writing provided under subsection 12.3.3 or, if no time period is specified, then within thirty (30) days from the end of the warranty period.  It shall be understood that in effecting the replacement, the Contractor shall also bear all costs involved in removing or replacing adjacent affected materials that may be disturbed and which shall be required in the complete restoration of the original finish.”

- Subsection 12.3 is amended by adding the following new subsection after subsection 12.3.6:

12.3.7	Acceptance of the Work by the Owner does not relieve the Contractor from correcting deficiencies which are missed at the time of drawing up the list of deficiencies or from correcting hidden deficiencies which become apparent during the warranty period.

ADD THE FOLLOWING:

- Standard Construction Document CCDC-2-2008 is further amended by adding the following new sections after Section 12:

PART 13 FREEDOM OF INFORMATION AND PROTECTION OF PRIVACY ACT

13.1 FREEDOM OF INFORMATION AND PROTECTION OF PRIVACY ACT

13.1.1 	All documents submitted to the Owner will be in the custody or control of, or become the property of, the Owner and as such are subject to the Freedom of Information and Protection of Privacy Act (B.C.) and may be disclosed pursuant to that Act or otherwise required by law.

PART 14 CONFIDENTIALITY

14.1 CONFIDENTIALITY

14.1.1	Except as provided for by law or otherwise permitted or required pursuant to this Contract (including, without limitation, section 13.1), the Owner and the Contractor will keep strictly confidential any information supplied to, obtained by, or which comes to the knowledge of the Owner and the Contractor as a result of the provision of the goods or performance of the services under this Contract, and will not, without the prior express written consent of the Owner, publish, release, disclose or permit to be disclosed any such information to any person or corporation, either before, during or after termination of this Contract, except as reasonably required to provide the goods or complete the services.

14.1.2	The Contractor shall return to the Owner all of the Owner’s property at the completion of the Contract, including any and all copies or originals of reports provided by the Owner.

14.1.3 	The Contractor shall not publish any statement, paper, photograph or document, or hold any ceremony with respect to the Contract or the Work performed under the Contract without the prior written approval of the Owner, which approval shall not be withheld unreasonably.

PART 15 SEVERABILITY

15.1 SEVERABILITY

15.1	Any provision of this Contract which is found to be illegal, invalid, void, prohibited or unenforceable will be:

(a)	Separate and severable from this Contract; and

(b) 	ineffective to the extent of such illegality, invalidity, avoidance, prohibition 	or unenforceability without affecting any of the remaining provisions of 	this Contract, which will remain in force, be binding upon the parties and 	be enforceable to the fullest extent of the law.

END OF SUPPLEMENTAL GENERAL CONDITIONS

APPENDIX B

ARCHITECTURAL, MECHANICAL, PLUMBING AND ELECTRICAL DRAWINGS

APPENDIX C

PROJECT SPECIFICATIONS

City of Coquitlam

PROPOSAL SUBMISSION FORM

RFP No. 23-008

General Contractor Services for City Hall Annex Third Floor Renovations

Proposals will be received on or before 2:00 pm local time on

Monday, January 30, 2023

(Closing Date and Time)

INSTRUCTIONS FOR PROPOSAL SUBMISSION

Proposal submissions are to be consolidated into one PDF file and uploaded through QFile, the City’s file transfer service accessed at website: qfile.coquitlam.ca/bid

1.	In the “Subject Field” enter:  RFP Number and Name

2.	Add files in .pdf format and “Send”

(Ensure your web browser remains open until you receive 2 emails from QFile to confirm upload is complete.)

Proponents are responsible to allow ample time to complete the Proposal Submission process. If assistance is required phone 604-927-3060.

| Legal Name of Proponent |  |
| --- | --- |
| Contact Person and Title |  |
| Business Address |  |
| Telephone |  |
| Email Address |  |

- DEPARTURES AND AWARD

| - CONTRACT - I/We have reviewed the City’s Standard Terms and Conditions - Purchase of Goods and Services and would be prepared to enter into in an agreement that incorporates the City’s Standard Terms and Conditions, amended by the following departures (list, if any): |  |
| --- | --- |
| Section | Requested Departure(s) / Alternative(s) |

- SERVICES - I/We have reviewed the Scope of Services as descibed in this RFP and are prepared to meet those requirements, amended by the following departures and additions (list, if any):

Requirements – Requested Departure(s) / Alternate(s) / Addition(s)

| - AWARD - For eligibility of award, the City requires the successful Proponent to complete and have the following in place before providing the Goods and Services. |  |
| --- | --- |
| - WCB - WorkSafe BC coverage in goodstanding and further, if an “Owner Operator” is involved, personal operator protection (P.O.P.) will be provided: | WCB Registration Number: |
| - Prime Contractor - Acceptance of Prime Contractor Designation for the Services: Prime Contractor Designation Form | Qualified Coordinator: Contact Number: |
| - Insurance – Provide Insurance coverage as per the City's Standard Insurance Form |  |
| - Vendor Info - Complete and return the City’s Vendor Profile and Electronic Funds Transfer Application (PDF) |  |
| - Business License - A City of Coquitlam or Tri Cities Intermunicipal Business License |  |
| - Contract – Acceptance of the City Contract using the CCDC 2-2008 documentas supplimented by the City’s Supplementary Conditions to CCDC 2 - 2008 |  |
| As of the date of this Proposal, we advise that we have the ability to meet all of the above requirements except as follows (list, if any): |  |

- CORPORATE

- CAPABILITIES, CAPACITY AND RESOURCES - Proponents to provide information on the following (use the spaces provided and/or attach additional pages, if necessary):

- Structure of the Proponent, background, how many years they have been in business and organizational history (e.g. mission, vision, corporate directions, years in business, etc.):

- Proponent is to state relevant experience and qualifications as to the Services requested in the RFP:

- Proponent is to provide a narrative as to their demonstrated ability to provide the Services requested in the RFP :

- Proponent is to describe their capabilities, resources and capacities, as relevant to the Services requested in the RFP: This includes their capacity to take on this project in regards to other work the Proponent may have ongoing:

| - REFERENCES – Proponent shall be competent and capable of performing the Services requested and successfully delivered service contracts of similar size, scope and complexity. The City reserves the right to contact any person(s), agency(ies) or firm(s) not listed as part of an independent review (use the spaces provided and/or attach additional pages, if necessary): |  |
| --- | --- |
| Reference No. 1 |  |
| Description of Contract |  |
| Size and Scope |  |
| Work Performed |  |
| Start Date |  |
| End Date |  |
| Contract Value |  |
| Project completed on budget |  |
| Project completed on schedule |  |
| Reference Information | Company |
|  | Name: |
|  | Phone Number: |
|  | Email Address: |

| Reference No. 2 |  |
| --- | --- |
| Description of Contract |  |
| Size and Scope |  |
| Work Performed |  |
| Start Date |  |
| End Date |  |
| Contract Value |  |
| Project completed on budget |  |
| Project completed on schedule |  |
| Reference Information | Company |
|  | Name: |
|  | Phone Number: |
|  | Email Address: |

| Reference No. 3 |  |
| --- | --- |
| Description of Contract |  |
| Size and Scope |  |
| Work Performed |  |
| Start Date |  |
| End Date |  |
| Contract Value |  |
| Project completed on budget |  |
| Project completed on schedule |  |
| Reference Information | Company |
|  | Name: |
|  | Phone Number: |
|  | Email Address: |

| - KEY PERSONNEL – Proponent proposes the following key personnel for the Services stated in the RFP. No changes, additions or deletions are to be made to these Key Personnel without the City’s written approval. |  |  |  |  |
| --- | --- | --- | --- | --- |
| LINE ITEM | NAME | TITLE/POSITION | EXPERIENCE AND QUALIFICATIONS | YEARS WITH YOUR ORGANIZATION |
| (use the spaces provided and/or attach additional pages, if necessary) |  |  |  |  |

| - SUB-CONTRACTORS - The following Sub-contractors will be utilized in provision of the Services and will comply with all the terms and conditions of this RFP. No changes, additions or deletions are to be made to these subcontractors without the City’s written approval: |  |
| --- | --- |
| Sub-Contractor No. 1 |  |
| Legal Name |  |
| Trade/Services Performed |  |
| Background and Experience |  |
| Contact Information | Name: |
|  | Phone Number: |
|  | Email Address: |

| Sub-Contractor No. 2 |  |
| --- | --- |
| Legal Name |  |
| Trade/Services Performed |  |
| Background and Experience |  |
| Contact Information | Name: |
|  | Phone Number: |
|  | Email Address: |

| Sub-Contractor No. 3 |  |
| --- | --- |
| Legal Name |  |
| Trade/Services Performed |  |
| Background and Experience |  |
| Contact Information | Name: |
|  | Phone Number: |
|  | Email Address: |

| - HEALTH AND SAFETY |  |
| --- | --- |
| - Confirm the Proponent has a written safety program in place that meets the requirements of WorkSafeBC? |  |
| ☐ Yes | ☐ No |
| - Is your company COR (Certificate of Recognition) certified with respect to WorkSafeBC? |  |
| ☐ Yes | ☐ No |

- TECHNICAL

- APPROACH and METHODOLOGY Summarize the key features of your Proposal and the Technical Approach to be used. Provide a brief description the various components required for successful completion of the work.

- Delivery, Set-Up and Execution - Proposals should address the plan for the delivery, set up and execution of the work; as well as the disposal, recycle or reuse for the surplus materials. Include any safety and pedestrian control measures.

- Quality Assurance - Provide the measures the Proponent will use to maintain quality control for the Services being performed.

- Risk Factors - Describe the risk factors anticipated and how the Proponent intends to mitigate these.

- Safety - Proponent is to state how they will address safety on the work site.

- Disposal and Recycling - Provide details on all disposal location and recycling location and procedures.

| - Completion Date |  |
| --- | --- |
| - The Proponent states that they are available and ready to start this work and confirms the work shall be completed on or before July 28, 2023. This date will be an important consideration in the evaluation. |  |
| ☐ Yes | ☐ No |
| - If Proponent has stated NO, please state date and explanation as to proposed completion date: |  |

| - PRELIMINARY CONSTRUCTION SCHEDULE Indicate schedule with bar chart with construction durations but not limited to. Contractor to add activities with durations as required. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONSTRUCTION ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prior to the start of construction, the Contractor will be required to provide a detailed CONSTRUCTION SCHEDULE ‘Gantt Chart’ Schedule in a MS Project format. Subsequently, the Contractor is to provide an updated construction schedule with each progress claim. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commence Construction Onsite February 20, 2023 or earlier |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Substantial completion date July 14, 2023 or earlier |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total completion date July 28, 2023 or earlier |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed Disposal Site: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- FINANCIAL

| - PRICE - Prices proposed are to be all inclusive; therefore, include all labour, material, tools, equipment, transportation, fuel, supervision, disposal fees, permit fees and any other items required for provision of the services (exclude GST). Fill in all sections, if price is included in another section state included in section x: |  |  |  |
| --- | --- | --- | --- |
| ITEM | SCOPE OF WORK | Unit of Measure | PRICE (exclude GST) |
|  | Demolition |  | $ |
|  | Disposal of material |  | $ |
|  | Construction of new conventional steel stud walls (see alternate method below) |  | $ |
|  | Plumbing works |  | $ |
|  | Electrical works |  | $ |
|  | Mechanical works |  | $ |
|  | Permits (electrical, plumbing, road closure, use of elevator etc.) |  | $ |
|  | Finishes |  | $ |
|  | Commissioning and training for operations |  | $ |
|  | Final clean up |  | $ |
|  | Other not listed above (specify) |  | $ |
| TOTAL |  |  | $ |

| - ADDITIONAL LABOUR RATES The following are rates for qualified trades personnel that would be used for valuing additional work and services beyond the scope of this RFP on an “as needed and when requested” basis. These rates are all inclusive without limitation, including all labour, wages, taxes and assessments, benefits payable in accordance with applicable laws, mobilization and demobilization, supervision, administration, small tool allowance including small tool rental, overhead and profit. |  |  |  |
| --- | --- | --- | --- |
| ITEM | SCOPE OF WORK | Unit of Measure | PRICE (exclude GST) |
|  | Project Manager |  | $ |
|  | Project Coordinator |  | $ |
|  | Site Superintendent |  | $ |
|  | Foreman |  | $ |
|  | Carpenter |  | $ |
|  | Concrete Finisher |  | $ |
|  | Plumber |  | $ |
|  | Electrician |  | $ |
|  | Labourer/Helper |  | $ |
|  | Structural consultant (coring of concrete slab) |  | $ |
|  | Other not listed above (specify) |  | $ |

- VALUE ADD Provide information on what makes your firm innovative, what is your competitive advantage, and what other services your firm provides that would assist or be of benefit to the City

- SUSTAINABLE BENEFITS AND SOCIAL RESPONSIBILITY - Describe all initiatives, policies, programs and product choices that illustrate your firm’s efforts towards sustainable practices and environment responsibility in providing the services that would benefit the City

- What policies does your organization have for hiring apprentices, indigenous peoples, recent immigrants, veterans, young people, women, and people with disabilities:

- What policies does your organization have for the procurement of goods and services from local small and medium sized business or social enterprises:

Attention Purchasing Manager:

- I/We, the undersigned duly authorized representative of the Proponent, having received and carefully reviewed all of the Proposal documents, including the RFP and any issued addenda posted on the City’s website www.coquitlam.ca/Bid-Opportunities , and having full knowledge of the Site, and having fully informed ourselves as to the intent, difficulties, facilities and local conditions connected to performing the Services, submit this Proposal in response to the RFP.

- I/We  agree to the rules of participation outlined in the Instructions to Proponents and should our Proposal be selected, agree to the City’s Standard Terms and Conditions - Purchase of Goods and Services  and will accept the City’s Contract as defined within this RFP document.

- I/We confirm that, if I/we am/are awarded the Agreement, I/we will at all times be the “Prime Contractor” as provided by the Worker's Compensation Act (British Columbia) with respect to the Services. I/we further confirm that if I/we become aware that another contractor at the place(s) of the Services has been designated as the “Prime Contractor”, I/we will notify the City immediately, and I/we will indemnify and hold the City harmless against any claims, demands, losses, damages, costs, liabilities or expenses suffered by the City in connection with any failure to so notify the City.

- I/We acknowledge receipt of the following Addenda related to this Request for Proposals and have incorporated the information received in preparing this Proposal.

| Addendum No. | Date Issued |
| --- | --- |

This Proposal is submitted this ____day of _______, 20______.

I/We have the authority to sign on behalf of the Proponent and have duly read all documents.

| Name of Proponent |  |
| --- | --- |
| Signature(s) of Authorized Signatory(ies) | 1. |
|  | 2. |
| Print Name(s) and Position(s) of Authorized Signatory(ies) | 1. |
|  | 2. |